## Iteration 1
Iteration 01 (21/05- 02/06)
STT | Screen/Non-screen | Ticket | Assignee |  | Issue | Progress | Esimation (man-day) | Start time | Deadline
1 | SC - Login | Degisn | HieuNH | Done |  |  |  | 2024-05-19 | 2024-05-20
|  | Front-end | HieuNH | Done |  | Done |  | 2024-05-21 | 2024-05-23
|  | Back-end | TuanLD | Done |  |  |  | 2024-05-20 | 2024-05-23
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
2 | SC - Forgot password | Degisn | HieuNH | Done |  |  |  | 2024-05-19 | 2024-05-20
|  | Front-end | HieuNH | Done |  |  |  | 2024-05-23 | 2024-05-24
|  | Back-end | TuanLD | Done |  |  |  | 2024-05-23 | 2024-05-25
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
3 | SC - Verify OTP | Front-end | HieuNH | Done |  |  |  | 2024-05-25 | 2024-05-26
|  | Back-end | TuanLD | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
4 | SC - Register | Front-end | HieuNH | Done |  |  |  | 2024-05-27 | 2024-05-28
|  | Back-end | TuanLD | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
5 | SC - CreateCampaign | Degisn | [5 empty] | 2024-05-21 | 2024-05-22
|  | Front-end | TruongVX | Done |  |  |  | 2024-05-23 | 2024-05-25
|  | Back-end | AnhTQ | Done |  |  |  | 2024-05-23 | 2024-05-25
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case | CuongLV | Done
6 | SC - UpdateCampaign | Degisn | [5 empty] | 2024-05-22 | 2024-05-23
|  | Front-end | TruongVX | Done |  |  |  | 2024-05-24 | 2024-05-26
|  | Back-end | AnhTQ | Done |  |  |  | 2024-05-23 | 2024-05-24
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
7 | SC - ViewListCampaign(Manage) | Degisn | [5 empty] | 2024-05-24 | 2024-05-25
|  | Front-end | TruongVX | Done |  |  |  | 2024-05-25 | 2024-05-26
|  | Back-end | AnhTQ | Done |  |  |  | 2024-05-25 | 2024-05-26
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
8 | NSC - DeactiveCampaign | Degisn
|  | Front-end |  | Done |  |  |  | 2024-05-25 | 2024-05-26
|  | Back-end | AnhTQ | Done
|  | Test Case | CuongLV | Done
9 | SC - View Project Details | Degisn | TruongVX | Done |  |  |  | 2024-05-21 | 2024-05-22
|  | Front-end | HieuNH | Done |  |  |  | 2024-05-23 | 2024-05-25
|  | Back-end | AnhTQ | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
10 | Create Project | Front-end | HieuNH | Done |  |  |  | 2024-05-23 | 2024-05-25
|  | Back-end | AnhTQ | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
11 | Update Project | Front-end | HieuNH | Done
|  | Back-end | AnhTQ | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
12 | SC - View List Project (Manage) | Degisn | TruongVX | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test Case( Integration Test, Acceptance Test) | CuongLV | Done
13 | NSC - Create Revenue | Degisn
|  | Front-end | [5 empty] | 2024-05-26 | 2024-05-27
|  | Back-end | AnhTQ | Done
Test Case
14 | SC - View List Revenue (Manage) | Design & Front-end
|  | Back-end | AnhTQ | Done |  |  |  | 2024-05-27 | 2024-05-28
15 | Navbar + Header Admin | Design & Front-end | TruongVX | Done
|  | Docs ( Report 1 ) | AnhHT | Done
|  | Docs ( Report 2 ) | AnhHT | Done

## Iteration 2
Iteration 02(03/06- 16/06)
STT | Screen/Non-screen | Ticket | Assignee | Status | Issue | Progress | Esimation (man-day) | Start time | Deadline
16 | SC - View List Account | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done |  |  |  | 2024-06-03 | 2024-06-04
|  | Back-end | AnhTQ | Done |  |  |  | 2024-06-03 | 2024-06-04
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
17 | SC - Filter Account List | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Back-end | AnhTQ | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
18 | SC - Create Account by Admin | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
18 | SC - Detail Account | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Back-end | AnhTQ | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
19 | SC - Update Account | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Back-end | AnhTQ | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) |  | Done
20 | NSC - Deactive Account | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done |  |  |  | 2024-06-03 | 2024-06-04
|  | Back-end | AnhTQ | Done |  |  |  | 2024-06-03 | 2024-06-04
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
21 | SC - View List News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
22 | SC - View List Processing News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
23 | SC - View List Approved News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Report 3 - Functional Requirements | CuongLV | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
24 | SC - View List Rejected News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
25 | SC - Filter News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Report 3 - Product Overview | CuongLV | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
26 | SC - Create News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Back-end | TuanLD | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
27 | SC - Update News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Back-end | TuanLD | Done |  |  |  | 2024-06-03 | 2024-06-05
|  | Report 4- System Design | CuongLV | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
28 | NSC - Delete News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
29 | NSC - Approve News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Report 4- System Design | CuongLV | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
30 | SC - Views Detail News | Degisn | CuongLV | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
|  | Report 3 - Product Overview | AnhHT | Done
|  | Report 3 - User Requirement | AnhHT | Done
|  | Report 3 - Functional Requirements | AnhHT | Done
|  | Report 3 - Non Funtional Requirement | AnhHT | Done
|  | Report 3 - Requirement Appendix | AnhHT | Done
|  | Report 4 - Database Design | AnhHT | Done
|  | Script Database | AnhHT | Done

## Iteration 3
Iteration 03 (17/06- 02/07)
STT | Screen/Non-screen | Ticket | Assignee | Status | Issue | Progress | Esimation (man-day) | Start time | Deadline
31 | SC - Create Project | Degisn | HieuNH | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
32 | SC - Update Project | Degisn | HieuNH | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
33 | SC- Project Information Details | Degisn | HieuNH | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
34 | SC - View by Status | Degisn | HieuNH | Done
|  | Front-end | HieuNH | Done
|  | Back-end | TuanLD | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
35 | SC - CREATE TRACKING | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
36 | SC - UPDATE TRACKING | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
37 | SC - VIEW LIST TRACKING | Degisn | CuongLV | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
38 | SC - LIST EXPENSE | Degisn | HieuNH | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
39 | SC - CREATE EXPENSE | Degisn | HieuNH | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
40 | SC - UPDATE EXPENSE | Degisn | HieuNH | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
41 | SC - DELETE EXPENSE | Degisn | HieuNH | Done
|  | Front-end | TruongVX | Done
|  | Back-end | AnhTQ | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
42 | SC - CLIENT PROFILE | Degisn | HieuNH | Done
|  | Front-end | HieuNH | Done
|  | Back-end | AnhTQ | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
43 | SC - PROJECT SPONSOR CREATE | Degisn | HieuNH | Done
|  | Front-end | CuongLV | Done
|  | Back-end | AnhHT | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
44 | SC - PROJECT SPONSOR LIST | Degisn | HieuNH | Done
|  | Front-end | CuongLV | Done
|  | Back-end | AnhHT | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
45 | SC - UPDATE PROJECT SPONSOR | Degisn | HieuNH | Done
|  | Front-end | CuongLV | Done
|  | Back-end | AnhHT | Done
|  | Test Case ( Unit Test, System Test) | AnhHT | Done
|  | Test case ( Integration Test, Acceptance Test) | CuongLV | Done
| DEPLOY | DEPLOY CODE | TuanLD | Done
|  | Report 4 - Database Design | AnhHT | Done
|  | Script Database | AnhHT | Done

## Iteration 4
324 |  |  | Iteration 04(03/07- 17/07)
| STT | Screen/Non-screen | Ticket | Assignee | Status | Issue | Progress | Esimation (man-day) | Start time | Deadline
| 1 | SC - Assign Manage | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 2 | SC - Add member | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
Test case( Integration Test, Acceptance Test)
| 3 | NSC - Delete Member | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
Test case( Integration Test, Acceptance Test)
| 4 | SC - BUDGET MANAGE | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
Test case( Integration Test, Acceptance Test)
| 5 | SC - ADD BUDGET | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhHT | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 6 | SC - DELETE BUDGET | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhHT | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 7 | SC - UPDATE BUDGET | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 8 | NSC - EXPORT PDF FINANCIAL REPORT | Degisn
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 9 | NSC - EXPORT EXCEL FINANCIAL | Degisn
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 10 | SC - DASHBOARD | Degisn | HieuNH | Done
|  |  | Front-end | HieuNH
|  |  | Back-end | TuanLD
Test Case( Unit Test, System Test)
Test case( Integration Test, Acceptance Test)
| 11 | NSC - AUTO UPDATE DONATION | Back-end | TuanLD | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT
Test case( Integration Test, Acceptance Test)
| 12 | SC - HOMEPAGE | Degisn | HieuNH | Done
|  |  | Front-end | HieuNH | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 13 | SC - CAMPAIGN PAGE | Degisn | HieuNH | Done
|  |  | Front-end | HieuNH | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 14 | SC - DETAIL PROJECT | Degisn | HieuNH | Done
|  |  | Front-end | HieuNH | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 15 | SC - USERPROFILE | Degisn | HieuNH | Done
|  |  | Front-end | HieuNH | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 16 | SC - ASSIGNED PROJECT LIST | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
| 17 | SC - CREATED NEWS LIST | Degisn | TruongVX | Done
|  |  | Front-end | TruongVX | Done
|  |  | Back-end | AnhTQ | Done
|  |  | Test Case( Unit Test, System Test) | AnhHT | Done
|  |  | Test case( Integration Test, Acceptance Test) | CuongLV
|  |  | Update UI, Figma | CuongLV | Done
|  |  | Update Report 3, 5 | CuongLV | Done
|  |  | Test round 2 IT | CuongLV | Done
|  |  | Report 4(Sequence Diagram) | AnhHT | Done
|  |  | Report 5 | CuongLV | In-progress
|  |  | Report 6 | CuongLV | In-progress
|  |  | Acceptance test | CuongLV | In-progress
|  |  | Test roud 3 IT | CuongLV | Done
|  |  | Unit Test | AnhHT | Done
|  |  | System Test | TruongVX