## WBS
Function/Screen | Feature | Sub Feature | Role1 | Role2 | .. | Screen Description | Level* | Planned | Status | SRS | Deadline | SRS Status | IT Cases | Deadline | IT Status | SDS | Deadline | SDS Status | BE | Deadline | BE Status | FE | Deadline | FE Status | ST Cases | Deadline | ST Status | Notes
User Login | Common | [5 empty] | Simple | Iteration 1 | IT-Done | AnhHT |  | Doing |  |  | Test Done |  |  |  | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
User Register | Common | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Reset Password | Common | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
User Profile | Common | [5 empty] | Medium | Iteration 1 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Change Password | Common | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Campaign List | Campaign | [5 empty] | Medium | Iteration 1 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Campaign Create | Campaign | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Campaign Detail | Campaign | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Campaign Update | Campaign | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
News List | News | [5 empty] | Medium | Iteration 1 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
News Create | News | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
News Detail | News | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
News Update | News | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Account List | Account | [5 empty] | Medium | Iteration 1 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Account Create | Account | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Account Detail/Update | Account | [5 empty] | Simple | Iteration 1 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Project List | Project | [5 empty] | Medium | Iteration 2 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Project Create | Project | [5 empty] | Complex | Iteration 2 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Project Detail/Update | Project | [5 empty] | Medium | Iteration 2 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Sponsor List | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | AnhTH |  | Done | CuongLV |  | Done |  |  | Test Done
Sponsor Create | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | AnhTH |  | Done | CuongLV |  | Done |  |  | Test Done
Sponsor Detail/Update | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | AnhTH |  | Done | CuongLV |  | Done |  |  | Test Done
Expense List | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Expense Create | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Expense Detail/Update | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Tracking List | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Tracking Detail/Update | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | AnhTQ |  | Done | TruongVX |  | Done |  |  | Test Done
Donation List | Project | [5 empty] | Simple | Iteration 2 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
HomaPage (Guest) | Common | [5 empty] | Complex | Iteration 2 | IT-Done | [9 empty] | AnhTQ |  | Done | HieuNH |  | Done |  |  | Test Done
ProjectList (Guest) | Common | [5 empty] | Complex | Iteration 3 | IT-Done | [9 empty] | AnhTQ, TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
ProjectDetail (Guest) | Common | [5 empty] | Complex | Iteration 3 | IT-Done | [9 empty] | AnhTQ, TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
CampaignDetail (Guest) | Campaign | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | AnhTQ |  | Done | HieuNH |  | Done |  |  | Test Done
(Function) Auto Update Donation | Donation | [5 empty] | Complex | Iteration 3 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
NewsList (Guest) | News | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | AnhTQ |  | Done | HieuNH |  | Done |  |  | Test Done
Newsdetail's (Guest) | News | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | AnhTQ |  | Done | HieuNH |  | Done |  |  | Test Done
Ranking | GuestFeature | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | AnhTQ, TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Ambassador List | GuestFeature | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | AnhTQ, TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Profile Page | GuestFeature | [5 empty] | Complex | Iteration 3 | IT-Done | [9 empty] | AnhTQ, TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
New Challenge | GuestFeature | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | AnhTQ, TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Challenge List | GuestFeature | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Challenge Detail | GuestFeature | [5 empty] | Complex | Iteration 3 | IT-Done | [9 empty] | AnhTQ, TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Profile Edit Page | GuestFeature | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
Donate History | UserFeature | [5 empty] | Medium | Iteration 3 | IT-Done | [9 empty] | AnhTQ, TuanLD |  | Done | HieuNH |  | Done |  |  | Test Done
(*) You can rate the functions' complexity level based on the number of fields on the screens or the number of transactions in the function, with the details as below
Simple | <=7 fields | <=3 transactions
Medium | <=15 fields | <= 7 transactions
Complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions can be counted actioning UI components, user or database access transactions

## Q&A
Date | Question | By | Priority | Due Date | Status | Note (answer, other notes)
2023-09-16 |  | KienNT | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open

## Issues
Date | Issue | Priority | Created | Owner | Due Date | Status | Notes
2024-06-23 | Hoàn thiện tracking theo template ( Phần tag WBS ) | Medium | AnhHT |  |  | Open
2024-06-23 | Report3: Use case diagram thì sau actor nên gộp search vào trong view list và không cần extend ra nhiều | Medium | AnhHT |  |  | Open
2024-06-23 | Use case về revenue sửa thành sponsor | Medium | AnhHT |  |  | Open
2024-06-23 | Report 4: Database Design: nên vẽ theo chiều ngang để cap lại nhìn đầy đủ và rõ hơn | Medium | AnhHT |  |  | Open
2024-06-23 | Report 3: Screen flow vẽ mỗi role 1 màu , các function create , search, delete, update đều ở trong view nên k cần extend ra | Medium | CuongLV |  |  | Open
2024-06-23 | Vẽ lại ERD theo chiều ngang | Medium | CuongLV |  |  | Open
2024-06-23 | Report 3: Sắp xếp các màn trong docs theo sreen flow | Medium | CuongLV |  |  | Open
2024-07-15 | Sequence diagram (Report 4) | Medium | TuanLD |  |  | Open
Open

## Defects
Date | Defect Description | Activity | Product | Product Details | Assigner | Assignee | Status | Updated | Notes
2024-10-13 |  | Review | Software/System |  |  |  | Pending | 2024-10-26
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending